## Standing Committee - Draft Mtgs
Suggested Date Range for Lab Cmte Meetings | Set/Projected Meeting Date | Meeting Materials Transmitted to Lab Cmte & Public Noticed (E+7 days) | Lab Cmte Meeting Date: First Review of Applicantion & Open of Public Comment | Public Comment (SBE Practice) # Days | Public Comment # Work Days | Standing Committee Close of Public Comment | Report Draft Period after Public Comment # Work Days | Report Draft Period Total # Work Days | Standing Committee Report Due to Department & Transmit Notice to Applicant for Draft Board Agenda Item | Board Agenda Item Submission Deadline | Board Meeting Dates Start | Board Meeting Dates End | Board Approval Notification to Applicant | No Board Approval - Comments on Next Steps
2023-03-08 | Set | 2023-03-01 | 2023-03-08 | Public Comment Complete | 10 | 2023-02-23 | 23 | 33 | 2023-03-27 | 2023-03-28 | 2023-04-18 | 2023-04-20
April 3-7, 2023 | Projected | 2023-04-05 | 2023-04-12 | 10 | 10 | 2023-04-22 | 4 | 14 | 2023-04-27 | 2023-04-28 | No May Board Meeting | No May Board Meeting
May 1-5, 2023 | Projected | 2023-04-24 | 2023-05-01 | 10 | 9 | 2023-05-11 | 8 | 17 | 2023-05-22 | 2023-05-23 | 2023-06-14 | 2023-06-15
June 5-9, 2023 | Projected | 2023-05-29 | 2023-06-05 | 10 | 9 | 2023-06-15 | 7 | 16 | 2023-06-26 | 2023-06-27 | 2023-07-19 | 2023-07-20
July 31-August 2, 2023 | Projected | 2023-07-24 | 2023-07-31 | 10 | 9 | 2023-08-10 | 8 | 17 | 2023-08-21 | 2023-08-22 | 2023-09-13 | 2023-09-14
September 6-8, 2023 | Projected | 2023-08-30 | 2023-09-06 | 10 | 8 | 2023-09-16 | 6 | 14 | 2023-09-25 | 2023-09-26 | 2023-10-18 | 2023-10-19
October 2-5, 2023 | Projected | 2023-09-25 | 2023-10-02 | 10 | 8 | 2023-10-12 | 8 | 16 | 2023-10-23 | 2023-10-24 | 2023-11-15 | 2023-11-16
November 6 or 8, 2023 | Projected | 2023-10-30 | 2023-11-06 | 10 | 9 | 2023-11-16 | 13 | 22 | 2023-12-04 | 2023-12-05 | 2024-01-24 | 2024-01-25
2023 STATE HOLIDAYS OBSERVED |  |  | March 22-23, 2023
2023-01-02 | New Year’s Day (Observed) |  | Executive Session - March 22, 2023
2023-01-16 | Martin Luther King, Jr. Day |  | Work Session - March 22, 2023
2023-02-20 | George Washington Day |  | Business Meeting - March 23, 2023
2023-05-29 | Memorial Day |  | April 18-20, 2023
2023-06-19 | Juneteenth (Observed) |  | Executive Session - April 18, 2023
2023-07-04 | Independence Day |  | Work Session - April 18, 2023
2023-09-04 | Labor Day |  | Board Retreat - April 19, 2023
2023-10-09 | Columbus Day & Yorktown Victory Day |  | Business Meeting - April 20, 2023
2023-11-07 | Election Day |  | June 14-15, 2023
2023-11-10 | Veterans Day |  | Executive Session - June 14, 2023
2023-11-22 | Close at noon |  | Work Session - June 14, 2023
2023-11-23 | Thanksgiving |  | Business Meeting - June 15, 2023
2023-11-24 | Day After Thanksgiving |  | July 19-20, 2023
2023-12-22 | 4 hours additional holiday time |  | Executive Session - July 19, 2023
2023-12-25 | Christmas |  | Work Session - July 19, 2023
2024 STATE HOLIDAYS OBSERVED |  |  | Business Meeting - July 20, 2023
2024-01-01 | New Year’s Day (Observed) |  | September 13-14, 2023
2024-01-01 | Martin Luther King, Jr. Day |  | Executive Session - September 13, 2023
2024-02-19 | George Washington Day |  | Work Session - September 13, 2023
2024-05-27 | Memorial Day |  | Business Meeting - September 14, 2023
2024-06-17 | Juneteenth (Observed) |  | October 18-19, 2023
2024-07-04 | Independence Day |  | Executive Session - October 18, 2023
2024-09-02 | Labor Day |  | Work Session - October 18, 2023
2024-10-14 | Columbus Day & Yorktown Victory Day |  | Business Meeting - October 19, 2023
2024-11-05 | Election Day |  | November 15-16, 2023
2024-11-11 | Veterans Day |  | Executive Session - November 15, 2023
2024-11-20 | Close at noon |  | Work Session - November 15, 2023
2024-11-21 | Thanksgiving |  | Business Meeting - November 16, 2023
2024-11-22 | Day After Thanksgiving
2024-12-24 | 4 hours additional holiday time
2024-12-25 | Christmas